Test Specification

Issue 1

TABLE OF CONTENTS

0	Preface	1

0.1	Purpose of this document	1

0.2	Use of this document	1

0.3	Overview	2

0.4	Testing within IDA	2

1	Introduction	4

1.1	Purpose	4

1.2	Scope of testing	5

1.3	Definitions, Acronyms and Abbreviations	6

1.4	References	6

1.5	Overview	6

2	TEST PLANNING	8

2.1	Test items	8

2.2	Features to be tested	9

2.3	Features not to be tested	9

2.4	Approach	9

2.5	Item pass/fail criteria	10

2.6	Suspension criteria and resumption requirements	10

2.7	Test deliverables	11

2.8	Testing tasks	11

2.9	Environmental needs	11

2.10	Responsibilities	12

2.11	Staffing and training needs	12

2.12	Schedule	12

2.13	Risks and contingencies	13

3	TEST DESIGNS	14

3.1	Test Design Identifier	14

4	TEST CASE SPECIFICATION	16

4.1	Test Case identifier	16

5	TEST PROCEDURES	19

5.1	Test Procedure identifier	19

6	TEST REPORTS	21

6.1	Test Report identifier	21

Document Control	22

Document Signoff	22

Document Change Record	22

0	Preface

0.1	Purpose of this document

- This document is a generic Test Specification document for use by IDA Projects. It provides guidance and template material which is intended to assist the relevant management or technical staff, whether client or supplier, in producing a project-specific Test Specification document. It is also useful background reading for anyone involved in developing or monitoring the IDA Management System (IDA-MS).

0.2	Use of this document

- This Preface is addressed to the users of this generic document and is not meant to be retained in any project-specific Test Specification documents based on it.

- The remaining sections (numbered 1, 2, 3,…) constitute a template that should be used to construct the project-specific Test Specification document.

- Text in normal case is in the most part “boilerplate” that can be retained, amended or deleted in the document.

- Text in italics provides instructions on how to complete a section and should be removed once the section is written.

- The template should be used pragmatically, that is - where a section is not relevant it should be omitted. Conversely, the material contained in this document is not necessarily exhaustive; if there is a subject that is relevant to the IDA Project, but is not included in this document, it should still be included.

- This document has been prepared using MS Word 97.  The following variables are currently recorded as File “Properties” under MS Word.  They may be modified by that means or overwritten directly at each occurrence in the document, at the discretion of the user.

| a. “Summary” Properties |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Title | Type of document (i.e. Test Specification) |  |  |
|  | Author | Author(s) of document |  |  |
|  | Keywords | Document reference (i.e. IDA-MS-TS) |  |  |
| b. “Custom” Properties |  |  |  |  |
|  | Proj Id | Short mnemonic of IDA Project (set, in this document, to “Project Id”) |  |  |
|  | Project | Full name of IDA Project (set, in this document, to “Template for IDA Project”) |  |  |
|  | Contr Id | Short identifier of contract (set, in this document, to “Contract Id”) |  |  |
|  | Contract | Full name of contract (set, in this document, to “Template for specific development”) |  |  |
|  | Version | Issue number (currently Issue 1) |  |  |
|  | Date | Date of document (currently 17 January 2001) |  |  |

0.3	Overview

- This preface is for information only.

- This preface will therefore not be retained in the project-specific document.

- The remaining sections (numbered 1, 2, 3,…) constitute a template that should be used to construct the project-specific document.

- Text in normal case is in the most part “boilerplate” that can be retained, amended or deleted in the document.

- Text in italics provides instructions on how to complete a section and should be removed once the section is written.

- The template should be used pragmatically, that is - where a section is not relevant it should be omitted. Conversely, the material contained in this document is not necessarily exhaustive; if there is a subject that is relevant to the project, but is not included in this document, it should still be included.

0.4	Testing within IDA

- This document can be used for the two levels of testing – subsystem & system acceptance and can be used for testing systems as well as software-only projects. It may also be useful to set up a test specification for the reviewing of the User Guides. It should be read in conjunction with the Review & Test Management Plan document, which sets out the way in which the overall philosophy for testing of the system should be planned based around a characterisation of the system. This will consider factors such as, inter alia:

- The distributed nature of the architecture – is it a Federated, Distributed or Point-to-Point system?

- It is a thin client, fat client, multi-tier system and the implications of this for breaking down testing into stages?

- Is it a system that has been designed to have high resilience?

- How familiar are users with this system? How resilient has it to be to users making simple mistakes when they are using it?

- The loading on the system – for example how many parallel users might be using the system at the same time? What throughput in messages sent across the system might be experienced at peak times?

- Any implications from the nature of the complexity of any database that may be at the heart of the system or distributed around project participants?

- Is the system vulnerable to attack from outside? Could people subvert the system and disable it ability to carry out its defined task? What security measures have been built in to the system, such as to encrypt information or to authenticate users?

- Another factor that will have a significant impact on the scale and approach to testing is the development model that is being employed.

- The traditional system development lifecycle is represented in the Waterfall model. Each stage in development is based on the results of the previous stage, which is assumed to embody all the requirements and constraints of prior stages. Systems are therefore tested against their specifications, rather than the requirements which were considered when developing the specifications.

- The V model is a variation of the waterfall model. It recognises that systems should be verified against source requirements. Therefore system testing is carried out against the system requirement, and user acceptance testing is carried against the user requirement.

- Rapid Application Development (RAD) differs considerably from the above two models. RAD is typically carried out in a series of discrete time periods (“timeboxes”) in close collaboration with users. Only the time period is fixed; the functionality that is delivered in that time, and the effort expended, may vary. Testing verifies that the agreed functionality has been developed correctly, but there is also a strong emphasis on reviews to ensure that the discrete developments are progressing towards delivering a system which adequately meets the top-level business requirement.

- The aim here is to encourage people concerned with testing a system to pause and reflect on the nature of the system, its purposes and the risks associated with it. Well planned tests, that are targeted at the key issues, will have far more impact than a series of unplanned and incoherent tests of the system.

# Introduction

- This section should provide an overview of the entire document and a description of the scope of the system. Specific attention should be paid to the nature of the system from the IDA viewpoint. In effect what is the mission for the system? For example, this section should address question such as:

          - is this a system that is designed to collected information from different Member States that will go into Brussels for use in an operational sense, such as system which may track goods across Europe? or

          - is it a system that collects statistics and moves them in a common format into Luxembourg to Eurostat?

- The way the system is to be tested will depend upon the mission defined for the system.

- In describing the scope of the system it is important to recognise at this point the implications of how distributed the system is in operation as this will have a major impact upon the testing that is to be defined in this document. An IDA system that collects a specific statistic monthly is not likely to be tested in the same way as a system providing daily updates of the movement of animals across the borders of the European Union. Security risks will also need to be considered.

- One facet that should concern the author of the Test Specification is the degree to which the system that is being described is a federated, distributed or point-to-point architecture. Federated systems are essentially those which act as equals in providing and consuming information to and from the architecture. Distributed systems may have a master node, perhaps based on a star configuration, that is the single point of failure. Point-to-point systems can operate in a closely coupled relationship where bespoke protocols enable them to communicate with one another as their application software is activated.

- Another vital point is the degree to which the system has to be resilient to failure. Some systems may require to operate in support of law enforcement agencies and be required to operate on a 24 by 7 basis. Others can withstand downtime of several days before creating difficulties for their users. This aspect of the characterisation of the system is another important facet that needs to be addressed in this part of the document in order that the testing required can be planned, designed, specified and reported on correctly.

## Purpose

- This section should:

          - describe the purpose of this document, including the level of testing involved;

          - specify the intended readership of this document.

- It is useful to reflect in this section what the purpose is of a test specification. In the way this document has been constructed, in effect as a template for use on a wide range of IDA projects we have set out to take the reader through the planning, the process of designing tests, the specification of the detail of the tests and the procedures that govern how the tests are carried out. Finally we cover the form in which tests are reported. In laying out this form we are making an assumption that the basic development model that will be followed in the so-called waterfall approach. In practice that might not be the case as systems may follow the ‘V’ model or use Rapid Applications Development (RAD) as their basis.

- Of course it is vital to remember that this document, like the system, is always changing and developing. As the system moves into service so requirements will emerge from users for further enhancements – they have to be tested and accepted as the system is upgraded. This may mean that many sections in this specification change, sometimes to take out tests that are unnecessary as the software in question has not been altered in the new build of the system.

##### This document should be read by Project Managers, team personnel engaged in planning system testing and the EU project team to ensure that the right level of testing has been specified depending upon the characterisation of the system.

## Scope of testing

- This section should summarise the system features to be tested. The scale of the testing will depend upon many things about the characteristics of the system. For example, in a simple thin-client configuration the scale of the testing at the front end of the system might be quite simple and straightforward. However, the system may need to be subjected to detailed load tests to ensure that the server component can withstand the load placed on it.

- Testing may also need to vary depending upon the implementation language involved in the systems development. For example, where Java may be used it could be important to undertake specific tests on the run-time environment- or Java Virtual Machine (JVM) – into which the Java software will be loaded, compiled and executed. Some JVM have a self optimisation capability that enables the software to learn from the first time it is run and be faster on subsequent invocations – it is reported that it is possible to be up to 25% faster on a second run of the executable software. In any time-sensitive systems this could prove to be important.

- Security might be an issue for some IDA projects. Whilst statistics may be of little concern to criminals operating across Europe and out into the international stage, information on the movement of goods may well attract attention and be subject to attempts to delete for example information on a particular shipment as it contains illegal substances. For these types of systems there should be a greater emphasis on security and formal penetration testing looking for weaknesses in the system. This is an aspect of testing that may require specialist assistance and should be considered early on in the project planning stages.

- If the system simply supports the transmission, say once a week, of a simple spreadsheet full of statistics into Luxembourg and this can be done via email over a weekend then the scale of testing required will be considerably less. The scope of testing may require, for example, tests to be carried out over several weeks to ensure the system is reliable and operates as required.

## Definitions, Acronyms and Abbreviations

- This section should define all terms, acronyms and abbreviations used in this document. The following is a list of definitions for this template:

| Unit testing | Verification that each unit, e.g. module, subroutine meets the design. It should test every path and every line in each module. This is not addressed within this document as it is felt that suppliers will have their own approach to unit level testing in accordance with their own QA systems |
| --- | --- |
| Acceptance testing | Validation that the system meets the user requirements |
| Integration testing | Verification that the units can be correctly integrated into sub-systems |
| Release number | If the delivery is to be incremental then each delivery needs to be uniquely identified and the tests can then be allocated for each delivery |
| Security Model | The way in which the system provides security from internal or external unauthorised use |
| System testing | Verification that the system works successfully and meets the system/software requirements |

## References

- This section should provide a complete list of all the applicable and reference documents, identified by title, author and date.  Each document should be marked as applicable or reference.  If appropriate, report number, journal name and publishing organisation should be included.

## Overview

##### Section 1 is the introduction and includes a description of the project, applicable and reference documents.

##### Section 2 describes the test planning.

##### Section 3 contains the test designs.

##### Section 4 describes the test cases.

##### Section 5 contains the test procedures.

##### Section 6 describes the test reports.

# TEST PLANNING

- Testing needs to be planned. The Review and Test Management Plan document describes the global approach to testing, but this section will provide detail for the tests themselves.

- In planning tests a wide range of factors have to be taken into consideration. These may include:

- Performance requirements that emerge from the system specification, where response times or latency (delays) in the system delivering messages matter for example.

- Investigations of the system under low-loading conditions, such as when a single user is logged onto the system and if appropriate where larger numbers of users are using it in parallel.

- The architecture of the system and any security implications that may arise or need to be addressed. For example a two tier-thin client architecture will require a different range of testing to a fat client two-tier system or a three-tier architecture. Moreover security testing should address firewalls, operating system vulnerabilities and system administration controls.

- The distributed nature of the system and how test data might be made available to simulate ‘live’ data being passed over the network.

## Test items

- This section should identify the test items, such as test data, test rigs (hardware & software), test harnesses and any reporting tools looking at the results of the testing.

- Particular consideration should be given to the need to carry out tests on the Security Model that underpins access controls to the system if they are required. This may require obtaining external assistance to devise what are often referred to as Penetration Tests – in effect ways of trying to enter the system illegally. This may require obtaining specialist software tools to enable testing of passwords and system administration and firewall controls.

- References to other software documents, e.g. the Technical Design document, should be supplied to provide information about what the test items are supposed to do, how they work, and how they are operated. It is recommended that test items should be grouped according to release number if the delivery is to be incremental.

## Features to be tested

- This section should identify all the features and combinations of features that are to be tested.  This may be done by referencing sections of requirements or technical design documents.

- References should be precise yet economical, e.g.:

- 'the acceptance tests will cover all requirements in the User Requirement Document except those identified in Section 2.4';

- 'the unit tests will cover all modules specified in the Technical Design Document except those modules listed in Section 2.4'.

- Features should be grouped according to release number if delivery is to be incremental.

## Features not to be tested

- This section should identify all the features and significant combinations of features that are not to be tested and explain why. If it is not possible to test some features at their most appropriate level of testing but which will be tested at a later level, this information should be included here. An example is where volume testing cannot be tested as part of System testing, but will be tested as part of the Acceptance testing as only the User’s system will have sufficient data to test.

## Approach

- This section should specify the major activities, methods (e.g. structured testing) and tools that are to be used to test the designated groups of features.

- For example, this section will have to address whether or not a test environment needs to be created to simulate a heavy loading on a central server when it might be under high utilisation. This may require developing or purchasing some software that would simulate the client side interactions of a user or it may require this to be developed internally within the project.

- Similarly, the approach taken to testing the security features within the system should also be considered. Experts acknowledge that people intent on attacking a system will often try to find it weakest link, this may be through a badly configured firewall, its underlying operating system, the lack of authentication of users or the controls for accessing the database.

- Activities should be described in sufficient detail to allow identification of the major testing tasks and estimation of the resources and time needed for the tests.  The coverage required should be specified.

## Item pass/fail criteria

- This section should specify the criteria to be used to decide whether each test item has passed or failed testing. Critical functions that must work in the system should be identified. If any of these fail the system testing must be halted.

- It would be useful to introduce a capability to grade failures and then use these to decide if a number of failures in each category to decide if the system is at all acceptable. These categories and criteria should be consistent with any agreed contractual specifications and other higher level documents such as the Review and Test Management Plan. For example,

- Serious system failures would be deemed a ‘A’ failure. These might also include the inability of the system to fail in a controlled way – perhaps requiring a re-boot if a communications line failed etc.  Security problems or failure under load testing might also be considered category ‘A’ failures. A defined number of ‘A’ failures would halt testing.

- ‘B’ failures would be seen to be failures of the system to represent the functionality requested in the specification.

- Category ‘C’ failures would be those which showed inconsistencies in the operation of the system in areas such as the GUI displays.

- Category ‘D’ failures might be areas where minor problems exist with the system.

- Category ‘E’ failures would be ones where the specification might seem to be in variance with the requirements specification.

- It may be that the pass fail criteria would use a set number of these failures. An example might be:

- 5 category ‘A’ failures

- 10 category ‘B’ failures

- 20 category ‘C’ failures

- 40 category ‘D’ failures

- 50 category ‘E’ failures

- This might be an acceptance profile that would allow a system to be partially accepted through a first round of testing. This section should address the implications of load tests etc. If the system has to have security features then this section should also address what constitutes failure in this area.

## Suspension criteria and resumption requirements

- This section should specify the criteria used to suspend all, or a part of, the testing activities on the test items associated with the plan. The typical profile outlined in the last section could be used to decide if the system is acceptable or not. This section should specify the testing activities that must be repeated when testing is resumed.

## Test deliverables

- This section should identify the items that must be delivered before testing begins, which should include:

- test plan;

- test designs;

- test cases;

- test procedures;

- test input data & test environment;

- test tools, both proprietary and test reference tools.

- The use of tools from other IDA and OSN projects should be considered here, including Horizontal Actions and Measures and similar projects in other sectors; for instance, Test Reference Tools that simulate the other end of an information exchange in a specified-manner.

- This section should identify the items that must be delivered when testing is finished, which should include:

- test reports;

- test output data;

- problem reports.

## Testing tasks

- This section should identify the set of tasks necessary to prepare for and perform testing. This will include getting test data and setting up any communications links and preparing any systems that will be linked up for the testing activities. This will have to take account of the approach being taken to building the system, such as waterfall etc. This section should also identify all inter-task dependencies and any special skills required. It is recommended that testing tasks should be grouped according to release number if delivery is to be incremental.

## Environmental needs

- The test environment will have to reflect the approach being taken to building the system. The environment will be different depending upon whether or not the development is being carried out under waterfall, ‘V’ model or RAD. This section should specify both the necessary and desired properties of the test environment, including:

- physical characteristics of the facilities including hardware;

- communications software;

- system software, such as operating system;

- browser & server software where this is appropriate;

- any special software such as a Java Virtual Machine (JVM)

- mode of use (i.e. standalone, networked);

- security software, such as PKI;

- test tools;

- geographic distribution where appropriate.

- Environmental needs should be grouped according to release number if delivery is to be incremental.

## Responsibilities

- This section should identify the groups responsible for managing, designing, preparing, executing, witnessing, and checking tests. Groups may include developers, operations staff, user representatives, technical support staff, data administration staff, independent verification and validation personnel and quality assurance staff.

- The involvement of different “players” should be considered:

- Commission Services and EU Agencies, including the output of related programmes

- Member State Administrations

- Contractors

## Staffing and training needs

- This section should specify staffing and staff training requirements.

- Identify training options for providing necessary skills to be able to perform the tests at the level required for the project. This may mean, for example, providing

- some basic end-user training in the operation of the system, or

- an operating system, Systems Administrators course to enable the test team to configure the operating system correctly for the test to be carried out, or

- if testing of security features is required, some form of penetration testing course.

## Schedule

- This section should include test milestones identified in the software project schedule and all item delivery events, for example:

- delivery of the test harness and any test data required to create the test environment

- programmer delivers software for integration testing;

- developers deliver system for independent verification.

- This section should specify:

- any additional test milestones and state the time required for each testing task;

- the schedule for each testing task and test milestone;

- the period of use for all test resources (e.g. facilities, tools, staff).

- This section should also address the implications of failing to meet the schedule as resources may have been redeployed or vital test equipment may no longer be available. Contingencies should also be planned into the timetable where it is appropriate.

## Risks and contingencies

- This section should identify the high-risk assumptions of the test plan.  It should specify contingency plans for each. Risks may include technological, geographical or political issues. This section will also describe what should take place if one of the risks occurs; in other words what is the contingency and what impact would it have on the testing etc.?

# TEST DESIGNS

- A test design shows how a requirement or subsystem is to be tested. Each design will result in one or more test cases. The ‘design’ of a test is a vital aspect of getting tests set out correctly to verify the system.

- A particular input to test design will be to look at which approach to the development of the system was taken c.f. waterfall, the so-called ‘V’ approach and RAD or any other accepted approach. In a classic waterfall design the test designs will be different from those involved in a RAD development. Systems test designs should specify the test approach for each requirement in the System/Software Requirement document. In the case where the ‘V’ approach is used it is important to calibrate the test designs at each stage in the process. System Acceptance test designs should specify the test approach for each requirement in the User Requirement document.

## Test Design Identifier

- The title of this section should specify the test design uniquely.  The content of this section should briefly describe the test design and its intended purpose. Key inputs should also be identified, as should external dependencies.

### Features to be tested

- This section should identify the test items and describe the features, and combinations of features, that are to be tested. For each feature or feature combination, a reference to its associated requirements in the user requirement or system/software requirement or technical design documents should be included.

- Whilst it is essential to test what is often referred to as the required operation of the system, it is also vital to ensure that the system is also tested under what can be thought of as non-nominal situations, such as when the communications line fails or when there is a problem with the database etc. This is often when a systems performance can become erratic and create difficulties for users, who may not all be highly IT literate. In this case the operation of the system in explaining what problems have arisen and how the user should respond are crucial to the operational use of the system.

- If the testing that is to be carried out is ‘under loaded’ conditions it will be vital to specify a design that truly simulates a loaded system. It will be vital to have a representative set of queries being executed on the system in parallel. For example, the test design team may have the option to write a single, repeating test that looks at the most difficult search on the system, such as trying to find an item in a database, or they might write a test script that sees this query being one of many that are input to the system in parallel.

### Approach refinements

- This section should describe the results of the application of the methods described in the approach section of the test plan.  It will need to take account of whether or not the testing will be carried out under a waterfall, ‘V’ or RAD development approach.

- Specifically it may define the:

- component integration sequence (for integration testing);

- paths through the control flow (for integration testing);

- types of test (e.g. white-box, black-box, performance, stress etc).

- The description should provide the rationale for test-case selection and the packaging of test cases into procedures.  The method for analysing test results should be identified e.g. compare with expected output, compare with old results, proof of consistency etc. The tools required to support testing should also be identified.

### Test case identification

- This section should list the test cases associated with the design and summarise what is intended to be derived from these test cases.

### Feature pass/fail criteria

- This section should specify the criteria to be used to decide whether the feature or feature combination has passed or failed. This should be based upon the failure category model suggested earlier in this document.

# TEST CASE SPECIFICATION

- Test cases specify the inputs, predicted results and execution conditions. Each test case should aim to evaluate the operation of a key element or function of the system.

- Failure of a test case, depending upon the severity of the failure, would be catalogued as part of the overall evaluation of the suitability of the system as a whole for its intended use.

- Test cases can start with a specific ‘form’ that allows operator entry of data into the system. This needs to be mapped, if the architecture is based upon an n-tier solution, through the business logic and rules into the server systems with transactions being evaluated both in a ‘nominal’ mode where the transaction is a success and for those occasions when the transaction or ‘thread’ fails.   Test design may also require one or more test cases and one or more test cases may be executed by a test procedure.

## Test Case identifier

- The title of this section should specify the test case uniquely.  The content of this section should briefly describe the test case and the objectives of the test case. It should also identify the functions within the system that the test case will evaluate – both in terms of a successful operation and where errors occur.

### Test items

- This section should identify the test items.  References to other documents should be supplied to help understand the purpose of the test items, how they work and how they are operated. The test items may be:

- input data & information that is suitable for the test

- the execution environment

- the software ‘build’ of the component or subsystem under test

- configuration of the operating system

- configuration of any hardware, such as communications systems, that would be evaluated in the test.

### Input specifications

- This section should specify the inputs required to execute the test case.  File names, parameter values and user responses are possible types of input specification.  This section should not duplicate information held elsewhere (e.g. in test data files). This can be a very important area of the test specification if the system is to be tested ‘under load’. In this instance the input specifications may have to describe how the software that will mimic the human operator will be set up.

- For example, if the test case is to simulate the system working with 20 users operating in parallel then the transactions for each of the twenty operators will need to be defined. Moreover some form of randomisation of the transactions being started and completed will be required. So it may be necessary to specify the range of what is often referred to as ‘thinking time’ that may be used by an operator. Typically this may range from 2 to 20 seconds. Using contemporary testing software it is possible to create a synthetic environment in which 20 apparent users are using the system in parallel and to use the randomisation algorithm to vary the rate at which each user appears to initiate a search or action on the system.

### Output specifications

- This section should specify the outputs expected from executing the test case relevant to deciding upon pass or failure. For example, in testing ‘under load’ it will be important to measure the response time of the system to a specific query or range of queries that are felt to provide a representative load on the system. If the issue is to measure the length of time it takes for a message to be transmitted from source to destination then other measurements of the system performance will have to be taken into consideration.

- File names and system messages are possible types of output specification.

- This section should not duplicate information held elsewhere (e.g. in log files).

### Environmental needs

- These are the pre-conditions for the testing. It can cover how the test environment is set up, what configuration is required for the system etc.

Hardware

- This should specify the characteristics and configurations of the hardware required to execute this test case. If the system will be required to run on several platforms, there should be test cases for each one, until it can be shown that the results will be the same whatever the platform. An example would be where a standard-compliant Java Virtual Machine is to be used on all platforms.

Software

- This should specify the system and application software required to execute this test case. This should be defined in terms of a build file that contains the subsystem or system that is to be tested under configuration control.

Other

- This should specify any other requirements such as special equipment or specially trained personnel in an area such as testing security related to the integrity of the system.

### Special procedural requirements

- This section should describe any special constraints on the test procedures that execute this test case. For example, these may include organisational arrangements where multi-national or multi-organisational testing may involve special arrangements such as interchange agreements between project participants.

### Inter-case dependencies

- This section should list the identifiers of test cases that must be executed before this test case.  The nature of the dependencies should be summarised. This will ensure that testing does not get out of sync and start to test features of the system that are downstream of key functions.

# TEST PROCEDURES

- A test procedure describes how to carry out the test cases.

- Each test case will have a corresponding test procedure, though a single test procedure may execute one or more test cases.

## Test Procedure identifier

- The title of this section should specify the test procedure uniquely.

### Purpose

- This section should describe the purpose of this procedure.  A reference for each test case the test procedure uses should be given.

### Special requirements

- This section should identify any special requirements for the execution of this procedure. This may include other procedures that have to be performed before this one, e.g. setting up data, and ones that have to performed after, e.g. producing a report.

- Relevant test data files should be stated.

### Procedure steps

- This section should include the steps described in the subsections below as applicable.

Log

- This should describe any special methods or formats for logging the results of test execution, the incidents observed, and any other events pertinent to the test.

Set up

- This should describe the sequence of actions necessary to prepare for execution of the procedure. This may include the setting up of the test reference tool, although where an identical set-up is used by more than one test procedure, it may be more useful to create a separate procedure, which would be run before this procedure and be listed in the Special Requirements section above.

Start

- This should describe the actions necessary to begin execution of the procedure.

Actions

- This should describe the actions necessary during the execution of the procedure. It should also include the specific data to be input and the expected results.

- This is especially important where the user interface is being testing, e.g. for HTML and web-based applications, where data must be entered on the screen and the result cannot be seen in a log file. Consideration should be given to the use of screen prints.

- It may be useful to use a table like this:

| Step No | Action (including input data) | Expected results |
| --- | --- | --- |
| 1 | On Login screen, input user name and password. Click on OK | Succesful login |

Shut down

- This should describe the actions necessary to suspend testing when interruption is forced by unscheduled events.

Restart

- This should identify any procedural restart points and describe the actions necessary to restart the procedure at each of these points.

Stop

- This should describe the actions necessary to bring execution to an orderly halt.

Wrap up

- This should describe the actions necessary to terminate testing.

Contingencies

- This should describe the actions necessary to deal with anomalous events that may occur during execution. These may include where the expected results do not occur and a problem report has to be raised. This section should describe whether the test can simply be repeated or whether data would have to reset before the test can be re-run.

# TEST REPORTS

- This section may be extracted and produced as a separate document, to allow the descriptions of the testing to be finalised and the test specification document issued before the testing begins.

- The detail in each test report will depend upon the level of testing - e.g. subsystem, system, and acceptance. For example, for unit testing, each test report may cover a whole day’s testing; for acceptance testing each test procedure may have its own test report section.

## Test Report identifier

- The title of this section should specify the test report uniquely.

### Description

- This section should identify the items being tested including their version numbers.  The attributes of the environment in which testing was conducted should be identified.

### Activity and event entries

- This section should define the start and end time of each activity or event.

- One or more of the descriptions in the following subsections should be included.

Execution description

- This section should identify the test procedure(s) being executed. All the people involved and their roles should be identified, including those who witnessed each event.

Procedure results

- For each execution, this should record the visually observable results (e.g. error messages generated, aborts and requests for operator action).  The location of any output, and the result of the test, should be recorded.

- It may prove easiest to use the table as described in the test procedure section above with an extra column showing if the expected results were achieved. It may also be better to include the actual sheets used during the test as part of the test report, either scanned in or physically included although the latter would mean that the report would have to be in hardcopy.

Environmental information

- This should record any environmental conditions specific for this entry, particularly deviations from the nominal.

- Document Control

| Title: | Test Specification |
| --- | --- |
| Issue: | Issue 1 |
| Date: |  |
| Author: |  |
| Distribution: |  |
| Reference: |  |
| Filename: |  |
| Control: | Reissue as complete document only |

- Document Signoff

| Nature of Signoff | Person | Signature | Date | Role |
| --- | --- | --- | --- | --- |
| Authors |  |  |  |  |
| Reviewers |  |  |  |  |

- Document Change Record

| Date | Version | Author | Change Details |
| --- | --- | --- | --- |

This is important, as it may be necessary to plan ahead in this area to give time to develop some bespoke software to support detailed testing. This would need to be done as it may be difficult to move the system directly from development into the live environment without what is in effect some factory acceptance rather than in-situ acceptance testing.

These are often expensive pieces of software that require specialised skills to set them up. It is recommended that projects consider developing their own relatively simple test harness, but that they keep in touch with any Horizontal Actions & Measures (HAM) that might see a united approach being developed to creating test harnesses.

One facet of this would be to look at areas of the testing where a specific aspect of the overall performance needs to be tested. In client-server systems it may be that solutions may be based upon a range of technologies, such as Java. It may be that test designs have to reflect this by also addressing testing the performance of any Java Virtual Machine as this may impact the response time of the system from the user aspect. Moreover there may be other areas of the system that may require equal testing to ensure that no unnecessary overheads are being added in that might be reducing the possible performance of the system.